## Workbook Instructions
Welcome to your RTM Central Workbook. This is a self-serve guide designed to take your organization from initial decision to full-scale execution. RTM is a clinical and operational priority that requires leadership commitment and clear workflows.
1. This workbook follows a four-phase approach to ensure nothing is missed:
ALIGN: Get leadership on the same page regarding the "Why" and the "Who".
CLARIFY: Design every workflow decision before a single patient is enrolled.
ENABLE: Build staff capability through role-based training and pilot testing.
EXECUTE: Launch the program, measure results, and scale to a standard of care.
Estimated Time Investment: Expect 1-2 hours for the leadership team to complete the initial planning phases, plus ongoing time for training and weekly reviews.
2. The Golden Rules of RTM Success
To ensure this workbook leads to a high-performing program, adhere to these "non-negotiables":
Named Ownership: Every workflow step must have one named owner to prevent distributed ownership and missed charges.
Standardized Billing Cadence: Centralize billing entry—bill weekly for setup/device codes and monthly for treatment minutes.
Reinforce the 3 Key Behaviors: Every clinician must master - Offering the program, Enabling RTM before the patient leaves, and Checking the dashboard daily.

## Project Overview (Align)
Define Your Vision
What is your primary driver for implementing RTM?
Revenue & Retention: Reduce patient drop-off and generate RTM billing. | FALSE
Access & Hybrid Care: Serve patients between visits or those in remote areas. | FALSE
Clinical Outcomes: Improve adherence and decision-making via real-time data. | FALSE
Success Metrics Recommendations
Metric | Target Range
% Eligible Patients Enabled in RTM | 70-85%
Patients Enrolled in RTM Program | 70-85%
Met RTM Billing Milestones (98975/98985) | 85-90%
Revenue Gain | N/A
Align Checklist
Task | Completed Checkbox | Date Completed | Completed By
Primary goal agreed on by leadership | FALSE
Success metrics defined with targets | FALSE
Leadership commitment confirmed: RTM is a priority | FALSE

## Roles & Workflows (Clarify)
Make every workflow decision before enrollment starts.
RTM Operating Model Selection
Clinician-Driven Model (Recommended): Treating clinicians handle all enrollment and monitoring. | FALSE
Care Coordinator Model: A central coordinator manages monitoring | FALSE
Workflow Step | Owner
Patient app setup and tech support | Clincian Or Front Desk/Support Staff
Offer digital program at evaluation, Enroll in RTM, Activate | Clinician
Between-visit monitoring/alerts | Clinican or Care Coordinator
KPI reporting and accountability | Practice Manager
RTM Billing/EHR Documentation | Billing Lead
Decide Who Gets Offered RTM (RTM Eligibility/Expectation)
Enroll All: Every patient is offered RTM unless they opt out. Best for organizations with strong billing oversight and broad payor coverage. Seamless Clinical Decision Making | FALSE
Selective: Only enroll patients with confirmed RTM coverage. Best for organizations with narrow payor mix or conservative billing approach. Verify with your top payers on their RTM. | FALSE
Set Up Charge Capture & EMR Documentation
Code | Description | Billing Frequency | Key Rule
98975 | RTM Setup | Once per episode | Bill once patient achieves 2 days of activity. For hospital outpatient therapy departments: do not bill 98975 and 98977/98985 on the same day.
98985 | Device supply, 2–15 days | Once per 30-day period | Select 98985 OR 98977 — not both
98977 | Device supply, 16–30 days | Once per 30-day period | Select 98985 OR 98977 — not both
98979 | RTM treatment, 10–19 min | Once per calendar month | Select based on treatment minutes met
98980 | RTM treatment, 20–39 min | Once per calendar month | Select based on treatment minutes met
98981 | RTM treatment add-on, +20 min | Multiple times per month | Add on top of 98979 or 98980
Step 1: Confirm CPT codes are active in your Charge Master and EHR. Verify 98975, 98977, 98979, 98980, 98981, and 98985 are priced and loaded before go-live. If not, contact your billing team or EHR vendor now.
Step 2: Choose your EMR documentation location and structure:
Approach | Best For | Selection
Non-visit encounter note (Recommended) | For EMR’s/situations with flexible encounter types that allow charge capture/documentation without a scheduled visit. (eg. For adding Durable Medical Equipment) | FALSE
Add to existing/future follow-up visit notes | For EMR’s/situations where charge capture must be associated with a specific visit encounter | FALSE
⚠️ If using a follow-up visit for the interactive communication requirement, it must be documented clearly and cannot be double-billed with another CPT code during that visit.
Step 3: Set a standard billing cadence. Assign one person as the RTM Billing Owner who: pulls the Medbridge Billing milestone report, copies documentation to the EMR, and submits charges with a standard cadence.
Recommended Best Practice:
Who: Billing Lead manages charge entry centrally (not individual clinicians)
When: Weekly billing for Device Set Up (98975) and Activity (98985/98977) and Monthly billing at the beginning of the month for Treatment (98979/98980/98981)
Clarify Checklist
Task | Completed Checkbox | Completed Date | Completed By
Operating model selected and documented | TRUE
Patient Cohort identified | TRUE
CPT codes confirmed active in EHR Charge Master | TRUE
EMR documentation location selected and configured | TRUE
Weekly/Monthly billing cadence set with named ownership | TRUE

## Training Materials & Behavioral
Build capability by role, pilot before you scale, then measure and improve.
Training Need | Training Materials | Completed?
RTM Permissions in Medbridge | RTM Management" is toggled ON for all staff in Medbridge Settings. | FALSE
Medbridge Access | All of our team members have a login to Medbridge. | FALSE
Training | All of our team members have completed their Quick Start Guides | FALSE
Job Aides
Name | Who Uses It
Job Aide - RTM Getting Patients Started | Clinician - post at workstation
Job Aide - RTM Getting Patients Started with Care Coordinator | Care Coordinator
Job Aide - RTM Billing Guide | Billing Lead
Job Aide - 2026 RTM Billing Cheat Sheet | Billing Lead
RTM Patient Flyer | Front Desk/Support Staff
Do clinicans understand the 3 key behaviors to enable RTM success?
Offer the Program: Every eligible patient is offered the Medbridge GO app at evaluation. | FALSE
Enable RTM: Every eligible patient is enrolled in RTM with MB GO before they leave the clinic. | FALSE
Check RTM Dashboards Daily: Spend 5 minutes daily reviewing adherence, red flags and messages | FALSE
Enable Checklist
Task | Completed Checkbox | Completed Date | Completed By
All roles trained before go-live date | FALSE
3 key behaviors confirmed understood by all participating clinicians | FALSE
Job aids printed and posted at point of care | FALSE
Patient-facing materials prepared (Flyers/Scripts) | FALSE

## Clinical Workflow (Execute)
Launch, measure, fix what's broken, and make RTM the standard of care.
Metric | Target | Month 1 | Month 2 | Month 3
% Eligible Patients Enabled in RTM | >70%
% Patients Enrolled in RTM Program | >70%
% 1st Episodes Met RTM Activity Milestones (98975/98985) | >85%
% Met RTM Treatment Milestones (98979/98980) | >50%
Problem | Root Cause | Fix
Low Patient Enablement in RTM | Buy-in / Knowledge | Coach outlier clinicians on RTM Benefits, enrollment and education best practices
Low Patient RTM Enrollment | Inconsistent patient enrollment process | Assist in clinic; Mandatory follow up call
Missed RTM Billing Milestones | Monitoring breakdown | Hardwire daily monitoring with proactive messaging
High Claim Denials | Payor mix mapping | Update payor matrix; audit documentation.
Execute Checklist
Task | Completed Checkbox | Completed Date | Completed By
Go-live checklist completed before first patient | FALSE
KPIs reviewed at first post-launch team meeting | FALSE
First monthly billing run completed and denial rate reviewed | FALSE
At least one patient success story documented and shared | FALSE
Workflow adjustments made based on clinical feedback | FALSE

## Weekly Pulse (Once Live)
To ensure this tab drives the "3 Key Behaviors" and success metrics follow these best practices derived from the playbook:
Track the "Starting Gate": If enrollment is below 70%, the treating clinicians are likely not offering the digital program consistently during initial evaluations.
Verify Billing Milestones: By Week 4, you should see patients hitting the 2-day activity mark for Setup code 98975 2+ day activity code 98985
Document Wins Early: Don't wait for perfection; use the "Key Wins" column to record the first clinician to hit a billing milestone or the first patient success story to share with leadership .
Triage Issues Immediately: If the denial rate is high or billing milestones are missed, use the "Top Blocker" column to trigger a review of payor matrices or monitoring workflows .
Week | Date of Meeting | % Eligible Enabled (Target: ≥ 70%) | Patient Enrollment Rate (Target: ≥ 70%) | % Hitting Billing Milestones 98975/98985 (Target: > 85%) | Key Wins (Clinical or Financial) | Top Blocker / Friction Point | Action Item for Next Week
Week 1
Week 2
Week 3
Week 4
Week 5
Week 6
Week 7
Week 8