## Start Here
Skills Rollout Workbook
Your interactive companion to the Skills Self-Guided Rollout Playbook
This workbook walks you through the four-phase ACES Framework — Align, Clarify, Enable, Sustain — and gives you a place to capture decisions, assign owners, track progress, and monitor performance once your program is live. Each tab maps to a section of the playbook.
The ACES Framework
1 ALIGN | 2 CLARIFY | 3 ENABLE | 4 SUSTAIN
Secure leadership commitment and define what success looks like. | Design program structure, assignment plan, and monitoring workflow. | Train Admins, Preceptors, and Clinicians with role-specific resources. | Launch, troubleshoot, and establish Skills as an ongoing workflow.
How to Use This Workbook
● | Work through tabs in order: Align → Clarify → Enable → Sustain.
● | Use the dropdowns and yellow-highlighted cells to capture your decisions.
● | Each phase has a completion checklist — mark items 'Done' as you finish.
● | The Progress Dashboard below updates automatically as you work.
● | Use the Program Builder and Roster tabs to plan actual programs and assignments.
Your Progress
Phase | Items Complete | Total Items | Status
Phase 1: Align | 0 | 4 | Not Started
Phase 2: Clarify | 0 | 5 | Not Started
Phase 3: Enable | 0 | 5 | Not Started
Phase 4: Sustain | 0 | 6 | Not Started
💡 Tip: Status updates automatically based on the 'Status' dropdowns on each phase tab. Mark items 'Done', 'In Progress', or leave blank.

## Core Behaviors
Core Behaviors of Skills Success
Before you build a single program, confirm your organization is bought in on these non-negotiables. Use the 'Confirmed?' column to track agreement with your leadership team.
Behavior | Description | Confirmed?
Named Ownership | Every program must have ONE named Admin responsible for building, assigning, and monitoring it.
Assign Before Launch | Clinicians and Preceptors must both be assigned to a program before orientation begins — without this, evaluation cannot occur.
Review Structure First | Build and review program structure BEFORE assigning users. Mistakes are harder to fix once people are in the system.
Two Preceptors Minimum | Assign at least 2 Preceptors to every program to prevent evaluation gaps when one is unavailable.
Regular Dashboard Reviews | Review the Outcomes Dashboard on a regular cadence (biweekly or monthly) to identify Clinicians falling behind.
⚠️ Important: Preceptors Cannot Be Unassigned
Once a Preceptor is added to a program, they cannot be unassigned. Revoking their access requires removing the entire Preceptor role, which removes their evaluation access across ALL programs. Decide your Preceptor list carefully before you build.

## 1. Align
Phase 1: ALIGN
Get leadership on the same page — define why you're rolling out Skills and what success looks like.
Rank Your Primary Driver
Rank each driver from 1 (most important) to 4 (least important). Your top driver shapes internal messaging and which metrics matter most.
Rank (1–4) | Driver | Description
| Standardization | Replace inconsistent paper checklists with a single, structured digital program across all locations.
| Compliance & Audit Readiness | Maintain a timestamped, Preceptor-attributed record of every competency evaluation.
| Onboarding Quality | Ensure new Clinicians receive consistent training and evaluation regardless of who their Preceptor is.
| Visibility | Give managers and leaders real-time insight into where Clinicians are in their training without manual reporting.
Success Metrics & Targets
These four metrics define a healthy Skills program. Confirm targets with leadership — you'll track against them on the Sustain tab.
Metric | Why It Matters | Target Range | Your Target
% Clinicians assigned within first week of hire | Catches assignment gaps early — the most common rollout failure. | 90–100%
% Checklists completed on time | Indicates whether onboarding keeps pace with hiring. | 80–90%
% Required skills signed off by a Preceptor | Direct measure of audit-readiness. | 85–95%
% Programs with 2+ active Preceptors | Prevents single-point-of-failure on Preceptor availability. | 100%
✓ Complete This Phase When
# | Task |  | Status
1 | Primary driver ranked and shared with leadership.
2 | Success metric targets agreed on.
3 | Leadership commitment confirmed (Skills is an organizational priority).
4 | Named Admin identified for each planned program.

## 2. Clarify
Phase 2: CLARIFY
Design your program structure, assignment plan, and monitoring workflow BEFORE you build anything in the platform.
Decision 1: Program Organizing Principle
Choose ONE organizing principle for your programs:
Approach | Example | Your Choice
By Role | "Home Health RN Onboarding," "PT New Hire Orientation"
By Phase | Single onboarding program with checklists for Week 1, Week 2, Week 4
By Topic / Compliance | "Infection Control," "Patient Mobility Skills"
Decision 2: Program Naming Convention
Write your naming convention so future programs follow the same pattern (e.g., '[Role] – [Track] – [Year]'):
⚠️ Plan Preceptor Assignments Carefully
Preceptors CANNOT be unassigned from a program once added. Revoking access requires removing the entire Preceptor role, which removes their evaluation access across ALL programs. Decide your Preceptor list before you build.
Decision 3: Assignment Plan
Step | Decision | Your Answer
1 | Preceptors per program (minimum 2)
2 | Preceptor assignment level
3 | Collaborators (view-only): managers, educators, quality staff
4 | Email notifications to Clinicians when assigned
Decision 4: Monitoring Workflow
Element | Description | Your Plan
Monitoring Owner | One named Admin reviews the Outcomes Dashboard on a recurring basis.
Review Cadence | Biweekly or monthly recurring calendar block.
Escalation Criteria | When to escalate — e.g., no skills evaluated within 5 business days of assignment.
✓ Complete This Phase When
1 | Program structure and naming convention decided.
2 | Preceptor assignment plan documented (minimum 2 per program).
3 | Collaborators identified and ready to add.
4 | Monitoring owner and cadence assigned.
5 | Escalation criteria defined.

## 3. Enable
Phase 3: ENABLE
Train your Admins, Preceptors, and Clinicians. This is where most rollouts fail — make sure every audience is prepared.
Role-Specific Training Tracker
Role | What They Need to Know | Method | Status
Admin | Build and manage programs, assign users, review the Outcomes Dashboard. | Quick Start Guide + hands-on practice
Preceptor | Locate assigned Clinicians, evaluate skills, add Evaluator Notes. | 15-min live walkthrough (see below)
Clinician | Access checklists, complete self-assessment, review feedback. | Announcement email + orientation
Sample Clinician Announcement Email
Send 1–2 days before assigning the first cohort. Replace [bracketed] placeholders with your own values.
Subject: | Your Skills onboarding program starts [date]
Hi [Clinician name],
As part of your onboarding, you'll be using Medbridge Skills to complete your competency program. This replaces the paper checklists we've used in the past and gives you and your Preceptor a clearer view of your progress.
What to expect:
• | You'll receive an assignment notification on [date].
• | Your Preceptors are [Preceptor names].
• | Plan to complete your self-assessment within the first [X] days.
If you have questions, reach out to [Admin name].
Welcome aboard, | [Your name]
15-Minute Preceptor Walkthrough Agenda
Minutes | Topic |  | Status
2 min | Why Skills, why now — share your primary driver from Phase 1.
3 min | Locating your assigned Clinicians — log in and navigate to the dashboard together.
5 min | Evaluating a skill — demo a signoff, including how to add an Evaluator Note.
2 min | Documentation expectations — set the standard for when notes are required.
3 min | Q&A — answer questions; capture anything you can't answer for follow-up.
✓ Complete This Phase When
1 | All Admins trained on program building and assignment workflow.
2 | All Preceptors completed a live 15-minute walkthrough.
3 | Clinician announcement email customized and ready to send.
4 | Role-specific articles shared with each group.
5 | Common FAQs answered for your specific org context.

## 4. Sustain
Phase 4: SUSTAIN
Launch the program, monitor against the targets from Phase 1, and establish a recurring review cadence.
90-Day Success Metrics Tracking
Targets pull from your entries on the Align tab. Fill in actual values each month.
Metric | Target | Month 1 | Month 2 | Month 3
% Clinicians assigned within first week | ← Set on Align tab
% Checklists completed on time | ← Set on Align tab
% Required skills signed off by Preceptor | ← Set on Align tab
% Programs with 2+ active Preceptors | ← Set on Align tab
Troubleshooting Common Blockers
Problem |  | Root Cause |  | Fix
Clinicians not appearing in Preceptor's dashboard |  | Assignment gap — both not in the same program |  | Verify both are assigned to the same program in Education Management.
Checklists not being completed on time |  | Lack of awareness or competing priorities |  | Send reminders from the Outcomes Dashboard; escalate to manager.
Preceptor evaluations not being recorded |  | Preceptor unfamiliar with the evaluation workflow |  | Re-run the 15-minute walkthrough from Phase 3.
No visibility into progress after launch |  | Outcomes Dashboard not being reviewed regularly |  | Assign a monitoring owner and block recurring time on their calendar.
Audit trail incomplete or missing notes |  | Preceptors signing off without adding notes |  | Reinforce expectations; update skill descriptions to prompt documentation.
Monitoring Pulse (Ongoing — biweekly or monthly)
After 90 days, shift to this recurring cadence. Use the Outcomes Dashboard export to populate.
Period | Date | % Assigned On Time | % On Track | % Signed Off
Period 1
Period 2
Period 3
Period 4
Period 5
Period 6
Period 7
Period 8
✓ Complete This Phase When
1 | Phases 1–3 fully complete before first Clinician is assigned.
2 | First cohort of Clinicians assigned and notified.
3 | Preceptors confirmed active and able to see assigned Clinicians.
4 | Outcomes Dashboard reviewed at end of Week 1.
5 | Recurring monitoring cadence on the calendar.
6 | Workflow adjustments made based on early feedback.

## Program Builder
Program Builder
Plan your program → checklist → skill hierarchy here BEFORE you build in the platform. Each row represents one skill within a checklist within a program.
💡 How to use
Group rows by Program name (column B), then by Checklist (column C), then list each Skill (column D). Mark Required for skills that must be signed off for the program to count as complete. Use Notes for any context for Preceptors.
Program Name | Checklist Name | Skill | Required? | Notes
New Hire RN Onboarding | Week 1: Orientation | Complete HIPAA training module | Yes | Required by compliance
New Hire RN Onboarding | Week 1: Orientation | Tour the unit with charge nurse | Yes
New Hire RN Onboarding | Week 2: Clinical Skills | Demonstrate hand hygiene | Yes
New Hire RN Onboarding | Week 2: Clinical Skills | Operate IV pump | Yes | Preceptor observes 3 times

## Roster
Preceptor & Clinician Roster
Track who's assigned where. Confirm minimum 2 Preceptors per program BEFORE you assign Clinicians.
Preceptors
Name | Email / Login | Clinic / Region | Programs Assigned | Active? | Date Added
Clinicians
Name | Role | Hire Date | Program Assigned | Status | Assigned Date